## Planification
Project Phases | March |  |  |  | April |  |  |  | May | Mayo | Junio | Julio | June | Mayo | Junio | Julio | July | Mayo | Junio | Julio | August | Mayo | Junio | Julio | September | Mayo | Junio | Julio | October | Mayo | Junio | Julio | November | Mayo | Junio | Julio | December | Mayo | Junio | Julio
| w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4
1. Research & Planning
1.1 Project Planning: objectives | bar: w1
1.2 State of the Art Research | bar: w1 to w2
1.3 Cloud & IoT Study | bar: w3
1.4 ML Study for Licence Plate Recognition | bar: w4
1.5 Architecture Mock-Up | bar: w1 to w2
2. Development of Terminal Program
2.1 Pilot Terminal Program to Connect Devices | bar: w3 to w4
2.2 Development of APIs | bar: w1 to w2
2.3 Create Tests | bar: w3
3. Development of the Server
3.1 Pilot server program for data view | bar: w4 to w1
3.2 Development of APIs | bar: w2 to w3
3.3 Create Tests | bar: w4
4. Testing & Deployment in One Community
4.1 Cloud Infrastructure | bar: w1
4.2 Integration between Terminal & Server | bar: w2 to w3
4.3 Testing & Bug Fixing | bar: w4
4.4 Creation of Automatic Automatic Deployment Scripts | bar: w1
4.5 Production Testing | bar: w2
5. Deployment in Multi-Community
5.1 Development of the Multi-Community Adapter | bar: w3 to w4
5.2 Testing | bar: w1 to w2
5.3 Deployment | bar: w3 to w4
6. Structure of the document
6.1 Planification | bar: w1
6.2 Writing | bar: w2 to w1
6.3 Revision & Updates | bar: w2 to w4